## Filled Example
Scope item | Unit | Quoted qty | Quoted rate | Quoted total | Actual qty | Actual rate | Actual total | Variance | Taxable (Yes/No) | Reason | Approval reference | Invoice treatment
Monthly advisory retainer | month | 1 | 3700 |  | 1 | 3700 |  |  | No | As agreed in the SOW | SOW #SOW-2026-044 approved 2026-06-24. PO #NG-4471. | Bill as quoted
Additional hours beyond retainer | hour | 0 | 185 |  | 4.5 | 185 |  |  | No | Retainer balance exhausted on 2026-07-22; client approved continuing in writing | SOW #SOW-2026-044 approved 2026-06-24. PO #NG-4471. | Bill as a separate overage line at the agreed hourly rate
Discovery workshop, half day | session | 1 | 1200 |  | 1 | 1200 |  |  | No | As agreed in the SOW | SOW #SOW-2026-044 approved 2026-06-24. PO #NG-4471. | Bill as quoted
Travel, billed at cost | trip | 0 | 412.6 |  | 1 | 412.6 |  |  | No | Client approved on-site attendance after the SOW was signed | SOW #SOW-2026-044 approved 2026-06-24. PO #NG-4471. | Pass through at cost with receipts attached, no markup
Third-party data license | license | 0 | 89 |  | 1 | 89 |  |  | Yes | Client approved purchasing the dataset for the analysis | SOW #SOW-2026-044 approved 2026-06-24. PO #NG-4471. | Resell at cost on its own line; unlike the service lines this one may be taxable
Totals
Tax rate (illustrative; confirm your local rule) | 6%
Tax base (sum of taxable actual totals)
Tax
Final invoice total

## Blank Engagement Log
Scope item | Unit | Quoted qty | Quoted rate | Quoted total | Actual qty | Actual rate | Actual total | Variance | Taxable (Yes/No) | Reason | Approval reference | Invoice treatment
Totals
Tax rate (illustrative; confirm your local rule) | 6%
Tax base (sum of taxable actual totals)
Tax
Final invoice total

## Engagement Invoice Ledger
Invoice date | Invoice number | Scope summary | Invoice amount | Running total

## Retainer Drawdown
Retainer drawdown statement
Period covered | July 1 to July 31, 2026
Hourly rate | 185
Opening retainer balance (hours) | 20
Hours drawn this period | 24.5
Balance remaining (hours)
Overage hours
Overage amount
Replenishment trigger (hours) | 4
Next period (hours) | 20
Next period renews | August 1, 2026
Rollover policy | Unused hours do not roll over. State your policy in the SOW so the client is never surprised.