## Filled Example
Scope item | Unit | Quoted qty | Quoted rate | Quoted total | Actual qty | Actual rate | Actual total | Variance | Taxable (Yes/No) | Reason | Approval reference | Invoice treatment
Water heater, 50 gallon gas | unit | 1 | 1150 |  | 1 | 1150 |  |  | Yes | As quoted | Est. #EST-2026-204 approved 2026-07-19. | Bill as quoted. Materials, so sales tax applies in this example
Water heater installation labor | job | 1 | 650 |  | 1 | 650 |  |  | No | As quoted | Est. #EST-2026-204 approved 2026-07-19. | Bill as quoted. Whether labor is taxable depends on your state
Thermal expansion tank | unit | 0 | 165 |  | 1 | 165 |  |  | Yes | Local code requires an expansion tank on a closed system. Not visible at the quoting visit | Est. #EST-2026-204 approved 2026-07-19. | Add as a new approved line with the date the customer agreed
Main shutoff valve replacement | valve | 0 | 145 |  | 1 | 145 |  |  | Yes | Existing valve seized and would not close, so the new heater could not be connected safely | Est. #EST-2026-204 approved 2026-07-19. | Add as a new approved line. Photograph the failed part before replacing it
Old water heater removal and disposal | job | 1 | 125 |  | 1 | 125 |  |  | No | As quoted | Est. #EST-2026-204 approved 2026-07-19. | Bill as quoted
Municipal plumbing permit | permit | 1 | 175 |  | 1 | 175 |  |  | No | As quoted | Est. #EST-2026-204 approved 2026-07-19. | Show as a pass-through at cost so the customer can see it is not marked up
Less: diagnostic trip fee credited | credit | 1 | -95 |  | 1 | -95 |  |  | No | Trip fee was charged at the first visit and credited in full once the repair was booked | Est. #EST-2026-204 approved 2026-07-19. | Show as a credit line so the balance due is what the customer actually pays
Totals
Tax rate (illustrative; confirm your local rule) | 7%
Tax base (sum of taxable actual totals)
Tax
Final invoice total

## Blank Job Log
Scope item | Unit | Quoted qty | Quoted rate | Quoted total | Actual qty | Actual rate | Actual total | Variance | Taxable (Yes/No) | Reason | Approval reference | Invoice treatment
Totals
Tax rate (illustrative; confirm your local rule) | 7%
Tax base (sum of taxable actual totals)
Tax
Final invoice total

## Recurring Visit Ledger
Visit date | Invoice number | Scope summary | Invoice amount | Running total